## Some task to do
Metro Scanner System | MMC Project Tracker System | MMC Inventory System
Wait Finalization of MasterList | Add AR on qr generation + different QR per packages, track keystage/lot per package | This will be connected to MMC Tracker System's Database, this will allow the 2 system to communicate. Design and everything is TBD
Add as much details/visuals in reports as we can
Import via file excel file (schools, lots, keystage, packages, items, deliveries)
Billing-TBD might get connected to SAP will take forever to develop without SAP xD

## Progress of Project
THIS IS TBD
Project | Completion Percentage | MMC Tracker Pages | Percentage to System | Status | Progress | MMC Inventory Pages | Percentage to System | Status | Progress | MI Scanner Pages | Percentage to System | Status | Progress
MMC Tracker | 48.9% | Dashboard | 10% | 50% | 5% | Dashboard | 10% | 0% | 0% | Home | 5% | 90% | 4.5%
MMC Inventory | 0% | Projects | 5% | 80% | 4% | Projects | 5% | 0% | 0% | Inventory | 20% | 70% | 14%
MI Scanner | 66% | Deliveries | 15% | 80% | 12% | Deliveries | 15% | 0% | 0% | Cart | 20% | 70% | 14%
Overall | 38.3% | Billing | 20% | 0% | 0% | Billing | 20% | 0% | 0% | Customer | 10% | 70% | 7%
|  | Reports | 10% | 0% | 0% | Reports | 10% | 0% | 0% | Supplier | 0% | 0% | 0% | This might not be handled in the system
|  | Users | 5% | 60% | 3% | Users | 5% | 0% | 0% | History | 5% | 90% | 4.5%
|  | Overview | 5% | 60% | 3% | Overview | 5% | 0% | 0% | Users | 5% | 90% | 4.5%
|  | Schools | 3% | 80% | 2.4% | Schools | 3% | 0% | 0% | Syncing of App to Spreadsheet | 35% | 50% | 17.5%
|  | Lots | 3% | 80% | 2.4% | Lots | 3% | 0% | 0% | Total | 100% |  | 66%
|  | Keystage | 3% | 90% | 2.7% | Keystage | 3% | 0% | 0%
|  | Packages | 3% | 90% | 2.7% | Packages | 3% | 0% | 0%
|  | Items | 3% | 90% | 2.7% | Items | 3% | 0% | 0%
|  | Reports | 15% | 60% | 9% | Reports | 15% | 0% | 0%
|  | Total |  |  | 48.9% | Total |  |  | 0%

## Project Breakdown
Page | Scope | Percentage to System Completion | Status | Note | Target Date | Remarks
MMC Tracker | Dry run on sep 22 with opps department |  |  |  |  | Will follow initial plan if meeting with sir emil or SAP integration is impossible
Projects 1 | Filter all projects by date, agency, status | 3.5% | Pending |  | 2025-09-22
Dashboard 1 | Gross income = All Project total contract/All Paid Deliveries | 3.5% | Pending |  | 2025-09-22
Dashboard 2 | Cash flow = All Paid Deliveries per Date Paid | 3.5% | Pending |  | 2025-09-22
Dashboard 3 | Completion Progress % = All Pending Deliveries/All Delivered Deliveries + All Accepted Deliveries/2 | 3.5% | Pending |  | 2025-09-22
Dashboard 4 | Break down of completion progress = (per warehouse...region assigned to warehouse) | 3.5% | Pending |  | 2025-09-22
Dashboard 5 | Break down of completion progress per warehouse = per region | 3.5% | Pending |  | 2025-09-22
Dashboard 6 | Number of Active projects and total pending payments and paid deliveries | 3.5% | Pending |  | 2025-09-22
Dashboard 7 | Filters dashboard to per project | 3.5% | Pending |  | 2025-09-22
Projects 2 | CRUD Projects and Import Project by Excel File/ will be removed if SAP integration is possible | 3.5% | Pending |  | 2025-09-22
Deliveries 1 | Filter Deliveries by year, project, status | 6% | Pending |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
Billing 1 | Monitor if deliveries are paid or pending (Only if SAP integration is possible) with AI integration n8n | 12.5% | Pending |  | 2025-10-15 | Actual completion date will depend on meeting with sir emil
Testing/Debugging |  | 25% | Pending |  | 2025-12-31
Logs 1 | log users activity |  | Pending |  | 2025-12-31
Dashboard 8 | Visual representation of Key Performance Indicators of Projects: |  | Ongoing |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
Users 1 | CRUD users | 1.25% | Ongoing |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
Users 2 | user level roles | 1.25% | Ongoing |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
Reports 1 | Convert visual representation of dashboard to table view(printable) | 8% | Ongoing |  | 2025-10-15 | Actual completion date will depend on meeting with sir emil
Deliveries 2 | Generate QR code per package | 5% | Ongoing |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
Deliveries 3 | CUD Deliveries(If SAP integration is not possible) | 5% | Ongoing |  | 2025-09-22 | Actual completion date will depend on meeting with sir emil
QR Generator 1 | Generate QR code per package (will be grouped by lot or keystage)/ per package | 2% | Done |  | Done
QR Generator 2 | Generate AR with QR/ per keystage and lot | 2.5% | Done |  | Done
MI Scanner APP | Will be tested in production | 100%
Home 1 | Visual Representation of data in spreadsheet | 5% | Pending |  | 2025-10-15 | MI Master List will come from MI Team
Testing/Debugging 1 |  | 25% | Pending |  | 2025-12-31
Users 1 | Add and modify users | 3% | Pending |  | 2025-10-01
Inventory 1 | Sync with spreadsheet using appscript | 13% | Ongoing |  | 2025-10-15 | MI Master List will come from MI Team
Users 2 | User role | 3% | Ongoing |  | 2025-10-15 | MI Master List will come from MI Team
All page 1 | Search Function | 15% | Ongoing |  | 2025-10-15 | MI Master List will come from MI Team
Inventory 2 | Generate QR CODE in size for hang tags | 13% | Done |  | Done | This is done but might change the design
Cart 1 | Get item by scanning QR code, fetch from DB | 5% | Done |  | Done | This is done but might change the design
Cart 2 | Get customer name and details for quotation generation | 5% | Done |  | Done | This is done but might change the design
Worker 1 | Must have native feel to phones | 5% | Done | Will be optimized during testing and production | Done
Customer 1 | Add and modify customer details | 5% | Done |  | Done
History 1 | Get previous quotations | 3% | Done |  | 2025-10-15 | MI Master List will come from MI Team
MMC Inventory | THIS IS TBD (Will need wireframe/prototyping for fast implementation) | 0 |  | Will be developed while MMC project tracker is in debugging/testing phase | Will start upon meeting with sir emil | Will follow initial plan if meeting with sir emil or SAP integration is impossible
Dashboard 1 | List of Items(qty of items inputted on warehouse, pull out items in logistic,delivered items) |  | Pending |  | 2025-10-31
Dashboard 2 | Watch stock level, notifications via AI, future insights (only if sap is possible) can still be implemented on scale |  | Pending |  | 2025-10-31
Dashboard 3 | Items scanned by employee will be showed to admins dashboard to verify and accept items |  | Pending |  | 2025-10-31
Inventory 1 | CRUD items, qty |  | Pending |  | 2025-10-31
Inventory 2 | Integrate with MMC project tracker(outgoing is deducted to inventory qty) |  | Pending |  | 2025-10-31
Logistic 1 | Track which logistics will deliver the packages |  | Pending |  | 2025-10-31
Logistic 2 |  |  | Pending |  | 2025-10-31
Logistic 3 |  |  | Pending |  | 2025-10-31
Reports 1 |  |  | Pending |  | 2025-10-31
Users 1 | Add or Modify Users |  | Pending |  | 2025-10-31
Users 2 | User Roles |  | Pending |  | 2025-10-31
QR Generator 1 | Might add an anchor or something to incoming and outgoing packages |  | Pending |  | 2025-10-31
QR Generator 2 | When QR is scanned it will increase items count by package |  | Pending |  | 2025-10-31
QR Generator 3 |  |  | Pending |  | 2025-10-31
Testing/Debugging 1 |  |  | Pending |  | 2025-12-31

## Ivan Task
Date | Tasks | Remarks
2025-09-23 | Tested Project Tracker Pages and Added Button Function and Reponse -Deliveries -Lots | Fixed filters and add and edit buttons
2025-09-24
2025-09-25
2025-09-26
2025-09-27 |  | Saturday
2025-09-28 |  | Sunday
2025-09-29
2025-09-30
2025-10-01